## Slide 1
GROUNDWORK · HOW IT ALL FITS · 9 SEPTEMBER 2026
Three markets, one apparatus
What has been delivered and how firmly it stands, what each market has received, how a recording becomes something a client can rely on, what is ahead and dated, and who owns which part.
30
recorded conversations
5,011
quotable turns on the register
390
claims with a verdict
236
quotes on a client surface
Notes: THE ONE SENTENCE — Three markets built one working apparatus, and every number here was measured today.
Open on the four numbers, left to right. They are the funnel; the rest of the deck unfolds it.

## Slide 2
01 · WHAT THREE MARKETS DELIVERED
Three markets, and how firmly each one stands
Pryor
138
claims on the register
26
30
77
12
recorded conversations
22
documents received
Council Bluffs
113
claims on the register
21
19
66
9
recorded conversations
8
documents received
Hamina
105
claims on the register
16
12
74
9
recorded conversations
15
documents received
supported
contested or misframed
the client's own figure
unverified, held
Verdicts from the Claims Register; conversations from the corpus; documents from the delivered set · measured at build, 9 September 2026
Notes: THE ONE SENTENCE — Every market is an evidence base with its uncertainty on the surface.
Point at the bars. The grey is the honest part: what was said and has not yet been proven.

## Slide 3
02 · WHAT EACH MARKET HAS RECEIVED
What has actually reached each market
PRYOR
22 documents
COUNCIL BLUFFS
8 documents
HAMINA
15 documents
Market Impact Assessment
Citation Index
Proof Points Addendum
Story Spine
Interview overviews and notes
14
2
Interview guide and questions
2
Producer brief / timeline
7
Flagship film review
2
Opportunities for future research
Impact report scaffold (internal)
received
not yet
Read from the delivered set by filename; a number is a count where a market received more than one · measured at build, 9 September 2026
Notes: THE ONE SENTENCE — Three markets have received the same families of document, in the same order.
This is the slide that answers 'what have we actually given them'. Let it sit.

## Slide 4
03 · THE LADDER, BY RUNG
Where every deliverable stands, rung by rung
RUNG 0 · Evidence and Sources
Evidence & Claims Register
90%
continuous
Friction registers
85%
Aug 7 assessment
Pillar-Proof Matrix
60%
Aug 11-14 review
RUNG 1 · Story Spines
Story Inventory & Champion Map v0
70%
Aug 7 + rolling
8–12 story/champion profiles
5%
Aug 25 (Ham) / Sept 28…
RUNG 2 · Market reports
CB Impact Report (internal v0)
40%
Aug 7 assessment
Hamina Impact Report (internal v0)
55%
Aug 25 v1 / Sept 9
Pryor Impact Report (INTERNAL-ONLY v0)
35%
Aug 7 (findings only)
RUNG 3 · Cross-Market Synthesis
Master Synthesis Report (v0 shell)
30%
Aug 11-14 / early Oct
RUNG 4 · What [the client] receives
Executive Briefing (Kim)
40%
Aug 7 / early Oct
Storytelling Toolkit (Jules)
10%
early Oct
Video suite (Juno Collective)
10%
Aug 25 (Ham) / Sept 28…
Market Intelligence Playbook / Framework (Phase 4)
40%
Sept 9 v1 / Oct final
delivered or close
in flight
just begun
13 deliverables on 5 rungs; percent-complete is the project's own figure; folded items hidden · measured at build, 9 September 2026
Notes: THE ONE SENTENCE — The evidence rungs are complete; what remains is the client-facing top of the ladder.
Top rung is done; the bottom rung is what the client receives at the end. Read it downward.

## Slide 5
04 · HOW A RECORDING BECOMES A DELIVERABLE
From a conversation to a client surface
30
recorded conversations
INTAKE
transcribed, speakers named by ear, filed under one name
5,011
quotable turns
TURNS
every turn on the quote register with its speaker and its second
390
claims with a verdict
CLAIMS
supported, contested, the client's own, or held
236
quotes on a client surface
CLEARED
what clearance let through, traced to the tape
The claims, by verdict, across the three markets
79 supported
75 contested or misframed
19
217 unverified, held
supported
contested or misframed
the client's own figure
unverified, held
Block height is on a log scale so the first and last stage both read; the split is the whole register · measured at build, 9 September 2026
Notes: THE ONE SENTENCE — What reaches the client is a small, traceable fraction of what was said, on purpose.
Walk the four blocks. The drop from turns to claims is the discipline; the drop from claims to cleared is the clearance rule.

## Slide 6
05 · WHAT IS AHEAD
The next four weeks, on the calendar
week of 7 Sep
week of 14 Sep
week of 21 Sep
week of 28 Sep
week of 5 Oct
today
Pryor
9 Sep–13 Sep Pryor PRODUCTION shoot
Council Bluffs
22 Sep–26 Sep Council Bluffs PRODUCTION shoo
Hamina
9 Sep–10 Sep Finland announcement peg
22 Sep–26 Sep Hamina 2nd visit
Delivery gates
9 Sep Framework v1
25 Sep J5
28 Sep Pryor + Council Bluffs v1 edit
30 Sep J6
5 Oct Cross-market finals
field window
public peg
delivery gate
Read from the project's dated gates; weekends shaded; the dashed line is the build date · measured at build, 9 September 2026
Notes: THE ONE SENTENCE — Production and delivery are dated to the day; nothing here is aspirational.
Two production windows, then the delivery gates in a row. Point at the gap between them: that is where the finals get written.

## Slide 7
06 · WHO OWNS WHICH PART
What changes hands, and when
THE CONTRACTOR
JUNO
THE CLIENT
Deliverables and interview material
on payment
on delivery
The method's description
on payment
on delivery
Method built during, for the method
silent
no clause moves it
by its own agreement
What predates the engagement
stays
licensed alongside
The middle row is the apparatus. No clause moves it to Juno; the client's own agreement reaches for it. That is the conversation, and this is not a licensing position.
From the provenance map, which quotes the four documents themselves; nothing here says what a licence would look like · measured at build, 9 September 2026
Notes: THE ONE SENTENCE — The deliverables move; the method does not, by any clause either side has signed.
Do not sell this slide. Show it, name the middle row, and say the description is coming.